Stakeholder engagement strategy

| Stages | Objectives | Strategies |
| --- | --- | --- |
| Identification of stakeholders and initial contact | To ensure adequate representation from all relevant departments. To ensure stakeholders have the capacity to contribute to the project To alleviate concerns regarding the project | Face to face contact Opportunity for socialisation Informal contact first, followed by formal acknowledgement |
| Project briefing and initial engagement | To ensure clear understanding of project scope, aims and likely outcomes. To ensure clear understanding of roles and responsibility To generate a shared commitment and understanding for the project To generate momentum for change | Face to face brief meeting Summary of the project available in printed format Project details (electronic or printed) available upon request Incentives such as refreshments and stationary are useful to engage frontline staff. Clear statement of what the project is “not about” |
| Active involvement and engagement | To best utilise available expertise for project success To identify and involve change champions for project implementation To obtain feedback and comments in order to identify problems early | Selective identification and involvement of individuals when required Provision of incentives for change champions e.g. certificate of participation, professional development, presentations and publications Provision of incentives for feedback and comments such as a lucky draw |
| Maintenance of engagement | To provide updates and progress for proper project governance To maintain enthusiasm and commitment To encourage active participation | Regular updates through printed or electronic media such as newsletters, pamphlets and websites Brief face-to-face sessions during regular scheduled meetings such as in-service Innovative ideas such as a weekly quiz game |
| Project closure | To ensure dissemination of outcomes and successes To acknowledge participation and commitments from stakeholders To motivate stakeholders for continual improvement | Face-to-face brief presentation with senior management presence Formal acknowledgement such as grand rounds and certificates Acknowledgment of ward involvement such as provision of safety equipment and teaching aids |