# Implementation plan structure

Use this tool to plan changes and improvements to implement the National Model for Clinical Governance.

As with all implementation guide tools, the implementation plan tool is designed to be modified to suit the needs of your organisation. Adopt or adapt the headings or template as is useful to guide your planning process. Position implementation and reporting within your broader strategic and operational processes for supporting high-quality care.

The suggested headings cover three aspects of implementing the National Model for Clinical Governance (national model):

- Governance and roles

- Actions to address identified gaps in foundation good practice examples and warning signs as described in the national model (formatted as a separate document for each gap, but the headings can be used in any plan format)

- Tracking and reporting.

Gaps and associated actions to close them should be prioritised according to risk to care and/or the implementation process. Quantitative and qualitative information can be used to track implementation progress.

The tool includes an example of how the structure might be used to plan to close a good practice gap.

National model implementation: governance and roles

| Implementation planning overview |  |  |
| --- | --- | --- |
| Implementation purpose ‒ what will our organisation achieve by implementing the national model? |  |  |
| Our definition of high-quality care |  |  |
| Board implementation oversight role |  |  |
| Executive implementation role |  |  |
| Responsible operational and governance committees |  |  |
| How implementation progress is monitored and reported to the board |  |  |
| How patients, carers, consumers, clinicians and managers are engaged in implementation |  |  |
| Actions to increase governance and leadership maturity as we implement the national model Insert the implementation maturity scale ratings for the four aspects of your organisation’s governance and leadership maturity as documented in the implementation maturity scale under ‘C. Board and executive implementation governance and operational oversight’. |  |  |
| Aspect | Maturity level | Date of assessment |
| The board and executive share an understanding of the intent and content of the clinical governance model as a support for high-quality care. |  |  |
| The board and executive enact their respective clinical governance roles and responsibilities as required by the national model. |  |  |
| High-quality care is defined, governed and managed as a strategic and operational priority. |  |  |
| The board and executive evaluate national model implementation for its effectiveness in driving high-quality care. |  |  |
| Actions for aligning our roles with the national model’s roles supporting high-quality care |  |  |
| Aspect | Maturity level | Date of assessment |
| Consumer and patient representatives |  |  |
| Boards or equivalent |  |  |
| Executives or equivalent |  |  |
| Managers and clinical leaders |  |  |
| Clinicians ‒ includes the nursing, allied health and medical workforce |  |  |
| Non-clinical staff |  |  |
| Consumer and patient representatives |  |  |
| Actions for aligning our clinical governance framework document with the national model: |  |  |

National model implementation: gaps in foundation good practice examples

| FOUNDATION: |  |  |  |
| --- | --- | --- | --- |
| Good practice example Specify the good practice example (from the national model) where there is an identified practice gap in your organisation. |  |  |  |
| Gap and changes required What’s the gap and what type of change is required to close it? Introduce – Develop a new process Adapt – Modify an existing process What’s the scale of the change? Major change – Requires new, or changes to, policy and practice Minor change – Involves smaller updates, such as document revisions |  | What’s the gap? Type of change: Scale of change: |  |
| Is the change high priority? High-priority changes should be addressed in the first tranche of implementation changes. A high-priority change may be a major change, requiring substantial time and resources to address, and/or posing a significant risk to consumer and/or staff safety and wellbeing. |  |  |  |
| Actions to close gap/reduce risk | Lead(s) and committees/working groups | Timeframes | Progress Green: on time Amber: < 1 month behind schedule Red: > 1 month behind schedule |
| 1. |  |  |  |
| 2. |  |  |  |
| 3. |  |  |  |

## Example implementation plan

Below is an example of a populated plan for a gap in best practice to illustrate how the structure could be used.

| FOUNDATION: Leading systems and organisational culture |  |  |  |
| --- | --- | --- | --- |
| Good practice example Specify the good practice example (from the model) where there is an identified practice gap in your organisation |  | Good practice example 4 The board, executive and committees establish the systems and organisational culture to achieve consistently high-quality care and provide adequate resources for collaboration and accountability. |  |
| Gap and changes required What’s the gap and what type of change is required to close it? Introduce – Develop a new process Adapt – Modify an existing process What’s the scale of the change? Major change – Requires new, or changes to, policy and practice Minor change – Involves smaller updates, such as document revisions |  | What’s the gap? The board does not currently have a role in leading or monitoring organisational culture for high- quality care. Type of change: Introduce Scale of change: Major |  |
| Is the change high priority? High-priority changes should be addressed in the first tranche of implementation changes. A high-priority change may be a major change, requiring substantial time and resources to address, and/or posing a significant risk to consumer and/or staff safety and wellbeing. |  | High: Major change This is a significant governance gap and will take about 12 months to fully fill: to be addressed in the first tranche of changes. |  |
| Actions to close gap/reduce risk | Lead(s) and committees / working groups | Timeframes | Progress Green: on time Amber: up to a month behind schedule Red: more than a month behind schedule |
| 1. Set up an education and discussion session on the organisation’s quality culture to determine the board governance role, link culture development with the strategic plan and describe the culture of quality we want to achieve. | People and Culture Executive Board Quality and People Committee Full board | FY Quarter 1: August board meeting | Green |
| 2. Adapt the current operational plan for quality culture development to integrate the board role and aspirations. | People and Culture Executive Clinical Governance Director | FY Quarter 1 | Amber |
| 3. Integrate culture reporting into the Quality and People Committee agenda and create a board report from the culture report currently reported to the executive | People and Culture Executive Board Quality and People Committee | FY Quarter 2, October committee meeting | Green |
| 4. Evaluate progress with board quality culture oversight | People and Culture Executive Full board | FY Quarter 4, April board meeting | To start in November |

National model implementation: tracking and reporting

| - Implementation roles and reporting |  |
| --- | --- |
| Who is responsible for tracking and reporting on implementation progress? |  |
| What do key workforce groups and committees need to know about implementation progress and impact? |  |
| How will the information be shared? |  |
| How will feedback on implementation be actioned? |  |
| - Example measures of progress and impact (add your own as required) |  |
| Implementation progress (are we doing what we said we would do?) |  |
| % of implementation key actions started/completed on time. |  |
| Frequency and timeliness of clinical governance implementation reports to executive and governing body committees. |  |
| % risks and barriers to progress escalated through reporting, with remediation actions enacted. |  |
| Implementation outputs and impact (is it making a difference for patients and the workforce?) |  |
| Increased consumer and workforce understanding of what high-quality care looks like, their role in achieving it and how clinical governance supports their role. |  |
| Workforce and patient satisfaction with the impact of clinical governance model implementation. |  |
| Evidence of committee decisions that reference the national model. |  |
| Increasing clinical governance maturity within the foundations |  |
| Other impacts as listed within each step in the implementation guide. |  |
| Longer-term changes as seen in routinely collected or newly developed care quality or experience indicators (are we achieving consistently high-quality care?) |  |
| Increased compliance with good practice examples in each foundation that support high-quality care. |  |
| Measurable improvements in care quality (such as risk reduction, fewer complications, less unwarranted variation in care, improved outcomes, and greater workforce and patient satisfaction with care quality). |  |
| A more balanced approach to improving care that considers and shows improvement in all domains of high-quality care as described in the national model. |  |

© Australian Commission on Safety and Quality in Health Care 2026