Electronic medication management system implementation plan
ABCD

	 DocProperty KISClient \* charformat 

	 DocProperty KISSubject  \* charformat 

	March 2010



Electronic Medication Management Systems

Implementation Plan
Responsible:

[Insert name of project manager]
Project manager

Address:
Telephone:

Fax:

Email:
Date:
Version:

Approved by:

© Commonwealth of Australia 2011
The Australian Commission on Safety and Quality in Health Care encourages the not-for-profit reproduction of its documents — and those of the former Council — that are available on its web site, but requires acknowledgement of ownership.

You may download, display, print and reproduce this material (retaining this notice, and any headers and footers) for your personal, non-commercial use or use within your organisation. You may alter the contents of this material to suit the purposes of your organisation. All other rights are reserved.
Print

ISBN 978-0-9870617-5-1
Online
ISBN 978-0-9870617-6-8
Australian Commission on Safety and Quality in Health Care. Electronic Medication Management Systems —Implementation Plan, Australian Commission on Safety and Quality in Health Care, Sydney, 2011.

Requests for further authorisation should be directed to the:

Commonwealth Copyright Administration
Copyright Law Branch
Attorney-General's Department
Robert Garran Offices
National Circuit
BARTON ACT 2600

Or at www.ag.gov.au/cca 
The Australian Commission on Safety and Quality in Health Care can be contacted at:

Australian Commission on Safety and Quality in Health Care
GPO Box 5480
SYDNEY NSW 2001

Tel:

02 9263 3633
Fax:

02 9263 3613
Email:
mail@safetyandquality.gov.au
If calling from overseas:
Tel:
+61 2 9263 3633
Fax:
+61 2 9263 3613

Edited and produced by Biotext, Canberra

Project sponsor
[Insert name of project sponsor]

Project manager 

[Insert name of project manager]

Hospital(s) in scope
[Insert hospital(s)]

Version control
Document revision history

	Version
	Date
	Prepared by
	Comments

	
	
	
	

	
	
	
	

	
	
	
	

	
	
	
	

	
	
	
	


Distribution

	Copy number
	Release number
	Date issued
	Issued to

	
	
	
	

	
	
	
	

	
	
	
	


This is a managed document. For identification of amendments, each page contains a version date and a page number. Changes will only be issued as complete replacements covered by a release notice. This document has not been released for use until authorised by the last signatory.

Contents

7Preface



9Executive summary


101
Background and context


101.1
Background to the EMM project


101.2
The scope of the EMM system implementation


101.3
Strategic information and ICT context


111.4
Governance structure


122
EMM system implementation


122.1
Overview of the EMM system implementation


142.2
Project initiation


142.3
Implementation planning


152.3.1
Implementation planning study


172.3.2
Business process mapping and redesign


172.3.3
Policy development


172.3.4
Implementation sequence planning


182.3.5
Change management planning


202.3.6
Evaluation planning


232.3.7
Benefits management activities


252.3.8
Education and training


272.3.9
Project communications


292.3.10
Quality management


322.4
EMM system build and configuration activities


322.4.1
Design and acquisition of technical infrastructure


322.4.2
Software development


352.4.3
Building the technical environments


352.4.4
Nonfunctional testing


362.4.5
Configuration of EMM system content


362.4.6
Developing interfaces to key systems


372.4.7
User acceptance testing


392.5
EMM system implementation and go-live activities


392.5.1
Implementation checklist


422.5.2
Project control centre


422.5.3
Go-live roles and responsibilities


422.5.4
Pre- and post-go-live tasks


432.5.5
Escalation strategy


432.5.6
Managing the transition in a staged implementation


432.5.7
Rollback and project suspension strategy


432.5.8
Project team exit strategy and transition to support


443
EMM project governance


453.1
EMM project board


453.2
Roles of senior stakeholders


453.3
EMM project team


463.4
EMM reference group


463.5
Specialty subgroups and project assurance teams


463.5.1
Drug and therapeutics committee


463.5.2
Pharmacy subgroup


473.5.3
Medical subgroup


473.5.4
Nursing and midwifery subgroup


473.5.5
Allied health subgroup


483.5.6
Safety and quality subgroup


483.5.7
Information and communications technology (ICT) subgroup


494
Project plan


494.1
Key phases and milestones


504.2
Budget



524.3
Risk management


544.4
Issue management


565
Ongoing operations


565.1
EMM ongoing operations


565.1.1
Post-implementation review


565.1.2
Ongoing monitoring, evaluation and refinement


575.1.3
Consolidation of education and training


575.1.4
Ongoing vendor support


575.1.5
Benefits measurement


58Appendix 1
Business process maps


59Appendix 2
Terms of reference and minutes template


61Appendix 3
Project status report template




Tables

20Table 2.1
Stakeholder analysis


22Table 2.2
Evaluation framework


23Table 2.3
Example of baseline indicators for paper-based charts and expected changes when using an EMM system


25Table 2.4
Benefits register template


27Table 2.5
Education and training template


29Table 2.6
Communications plan template


31Table 2.7
Quality register template


32Table 2.8
Quality checklist


32Table 2.9
Implementation timeline template


35Table 2.10
Traceability matrix template


39Table 2.11
User acceptance testing (UAT) script template


41Table 2.12
Implementation planning checklist


46Table 3.1
Roles matrix template


46Table 3.2
EMM project team


51Table 4.1
Phases and milestones template


52Table 4.2
Budget and expenditure monitoring template


53Table 4.3
Risk assessment matrix


54Table 4.4
Risk register


56Table 4.5
Issue register




Figures
13Figure 1.1
EMM system implementation process flow


19Figure 2.1
Example stakeholder map


44Figure 3.1
Example project governance structure




Preface

An electronic medication management (EMM) system enables prescribing and recording of supply and administration of medicines to be completed electronically. EMM covers the entire hospital medication cycle, including prescribing by doctors; review and dispensing of medication orders by pharmacists; and administration of medications by nurses. EMM reduces medication errors through improved prescription legibility, dose calculation and clinical decision support. It enables best-practice information to be more readily available to prescribers and improves linkages between clinical information systems.
EMM systems can reduce medication errors, but they also have the potential to adversely affect safety and quality of care if the system is inadequately designed and implemented, and under-resourced. This risk is highlighted in a number of studies that show increased medication errors after poor implementation of EMM systems. With many Australian hospitals planning to implement EMM systems, it is essential that this risk is minimised by considering the international literature and learning from the experiences of early Australian EMM system implementations.

Implementing an EMM system within a hospital is a major transformational project that substantially affects clinical service delivery, hospital departments and the work of clinicians. It requires extensive pre-implementation planning, including initial scoping, developing a business case, evaluating and selecting an EMM system product, and conducting a detailed implementation planning study. It is essential that the project is adequately resourced, change is managed effectively, and the project has the endorsement and full support of the hospital executive and senior clinical staff.

How to use this template

This document is the key planning tool for hospital EMM system implementation, and accompanies Electronic Medication Management Systems — A Guide to Safe Implementation. This implementation plan is designed to be used as an electronic template. It provides the basis for a hospital’s EMM implementation plan, including appropriate heading structures and example tables. Hospitals should modify each section and table with their own data — instructional text and examples are provided in [square brackets and/or blue text] throughout the document.
Each hospital should develop a detailed baseline EMM implementation project plan and include this in Section 4, Project plan. The baseline plan is the project plan that is initially approved by the EMM project board. The phases of the plan and the tasks within each phase should be numbered for ease of cross-referencing (e.g. Phase 1 — Project initiation will include tasks 1.1, 1.2, 1.3, etc.). These phases and tasks in the project plan should be cross-referenced to sections throughout this template. Cross-referencing the project plan enables stakeholders to easily locate and understand the relationship between a section of the EMM planning template and the overall EMM implementation project plan.

Executive summary
[Write this section last.]

Aims and objectives
[List the aims and objectives of the EMM system implementation.]
Scope

[Outline the scope of the EMM implementation, including any key relationships and dependencies on other key systems. Outline what is not in scope.]

Context

[Provide the rationale for why an EMM system is to be implemented and the expected benefits. Include the breadth of services that will be involved in the implementation process and any known complexities that will need to be addressed.]
Project outline
[Outline:

phases, milestones and dates

resources required to implement the system.]

End point 

[Outline the end point or goal of the EMM system implementation.]

1
Background and context
1.1
Background to the EMM project
[Include relevant EMM background information here, including:
the business case approval process

any tender selection process

the outcome of the tender selection process

details of the selected EMM system.]

1.2
The scope of the EMM system implementation

[Provide a brief overview of the EMM implementation project, including:

phases, milestones and dates

project resources

whether there will be a pilot implementation

partner organisations; for example, any evaluation partner or change management partner

project dependencies; for example, other clinical systems, or information and communications technology (ICT) infrastructure projects that affect or will be affected by the EMM implementation

expected outcomes of the project.] 

1.3
Strategic information and ICT context

[Include details on whether the EMM system is part of a larger clinical system implementation or a separate EMM solution, and the rationale for this decision. 
Identify any relationships with other systems that include medication information and the nature of the relationships. For example:

where allergies and alerts are maintained

where diagnostic results are held

the existence of any specialised medication systems such as chemotherapy management systems

the relationship with the pharmacy dispensing system

the relationship with any medication reconciliation system

the relationships with any discharge referral or discharge summary systems.
Indicate whether the required ICT infrastructure is part of the EMM project or part of a separate project, and include a summary of the technology that will be required (e.g. wireless and mobile devices, fixed bedside devices, infotainment systems).]


1.4
Governance structure

[Provide a brief overview of the proposed governance structure for the project. Include details of: 

the project sponsor

the project board members and their roles (e.g. senior user, senior supplier)

the relationship with the organisation’s management structures and other program management functions (where EMM is part of a larger program of work)

the relationship with the governance of other dependent projects.

Note that more detailed information on the project governance structure is included in Section 3.]
2
EMM system implementation
2.1
Overview of the EMM system implementation

[This section provides an overview of the activities that will be undertaken as part of the EMM system implementation.]

The electronic medication management (EMM) system implementation will typically consist of five stages:
1.
project initiation

2.
implementation planning

3
EMM system build and configuration activities

4.
implementation and go-live activities
5
ongoing operations.
[If there are additional EMM implementation activities, include them here.]

The detailed content for each of these stages is outlined in Figure 1.1. 
[image: image1.jpg]Stage 1
Project initiation

Initial

Business
scoping case
Strategic D
context

|

IcT Funding
approval

infrastructure

Interfaces D

v

Governance
and project
management

v

Product
evaluation
and selection

No go

Change
readiness

Contract
management

End<——No go

Go Go

Stage 2
Implementation
planning

Implementation

planning study

Process
mapping

Policy
development

Implementation
sequencing

Change
management

Evaluation
planning

Benefits
management

Education

and training

Communications

Quality

management

|

—D—Go

Stage 3
EMM system build
and configuration

EMM system build

and configuration

Infrastructure
acquisition

Software
development

Build
environments

Nonfunctional
testing

Configure EMM
system content

Interface
development

User
acceptance
testing

|—Go

Implementation

activities

Implementation
checklist

Project control
centre

Roles and
responsibilities

Escalation
strategy

Managing
the transition

Rollback
strategy

Project team
exit strategy

|—Go

Stage 4 Implementation go-live activities

Rollout . Implement
Big bang ———>> P
strategy all areas
Staged
Implement
selected areas
Stage 5
Rewew Ongoing
operations
Reﬁne Ongoing Postimplementation
operations review
Impleme _ o
next areas Ongoing momt'orlng
and evaluation
Done? Continuous
adaptation
Database

maintenance

Software
upgrade

Control of
education and
training
Ongoing
1-4 =

Implementation stages vendor support

5 = Ongoing operating stage

= Decision point

Benefits
realisation





Figure 1.1
EMM system implementation process flow 
2.2
Project initiation

[Usually, project initiation will have been completed before starting the EMM system implementation. If this is the case, record a summary of the business case approval process, the approved funding, the results of any tender or procurement process, and the selected EMM system supplier.

If the project initiation forms part of this implementation plan, provide details of the planned process for developing and approving the business case, and any tender or procurement plans. Not all elements of the EMM implementation plan can be completed until the EMM solution supplier is known. If this is the case, the template should be completed in two stages.
See Chapter 3 of the Guide to Safe Implementation for more details on project initiation.]
2.3
Implementation planning

A well-planned EMM system rollout is essential for the success of the project. EMM implementation planning consists of:

the implementation planning study (IPS)
business process mapping and redesign

policy development

implementation sequence planning

change management planning

evaluation planning

benefits management activities 

education and training

project communications

quality management.

2.3.1
Implementation planning study

[The IPS is typically the first activity in EMM implementation. Sometimes the EMM system supplier will do the IPS and may have their own IPS template. In this case, use the checklist below to ensure all the issues are adequately covered in the EMM supplier’s IPS template.

If developing the IPS in-house, use the IPS checklist below to ensure all the issues are adequately covered in the IPS.  

Cross-reference the IPS activities to the baseline EMM implementation project plan, to be incorporated into Section 4 of this template. For example, include cross-references such as ‘The IPS can be found in Stage 1, tasks 10–85 of the project plan’.
See Section 4.1 of the Guide to Safe Implementation for more details on the IPS.]
	Implementation planning study (IPS) checklist

Typical IPS components comprise:

· a detailed EMM system implementation plan, including

all implementation tasks

software development activities

configuration and build activities

any lead EMM system implementation

EMM system rollout plans

· resources required from the vendor and the hospital

· project structures — governance, relationships, escalation processes

· project controls (e.g. PRINCE2 controls), including

scope and change management

configuration management

quality management

risk management

issue management

· technical infrastructure requirements, including the number of environments (e.g. production, test, training, development) and an environment management plan

· capacity requirements (e.g. numbers of users, user concurrency, data capacity)

· a gap analysis of the functional requirements and a plan to fill the gaps through software development

· an analysis of the interfaces required and a plan to deliver the interfaces

· project team EMM system training

· goal-state process mapping

· EMM system acceptance criteria

· a traceability framework

· EMM system education, and a training strategy and plan

· a data migration strategy and plan (if required)

· a testing strategy and plan, including 

user acceptance testing

non-functional testing

interface testing

integration (end-to-end) testing

stress and volume testing

· a software installation plan

· operational support and transition to support plan

· a list of all project deliverables

· contract payment milestones

· legislative and policy requirements

· a responsibility matrix.


2.3.2
Business process mapping and redesign

[Identify the extent to which current-state and future-state EMM process mapping is to be undertaken, the timing of these activities and who will undertake them. Section 4.2 of the Guide to Safe Implementation includes a list of specific EMM processes that require consideration, although there may be others.

The EMM system supplier may lead or undertake future-state process mapping as part of the IPS. The advantage of supplier participation in this process is their in-depth knowledge of the chosen EMM system and how this system is used elsewhere.

The development of current-state process maps ensures a thorough understanding of what happens now, and provides useful material to assist in consensus building. The process maps are also useful in supporting EMM communication materials and change management strategies. Include the process maps and their supporting narrative in Appendix 1 of this template.

Cross-reference the business process mapping and redesign activities to the baseline EMM implementation project plan in Section 4 of this template.]

2.3.3
Policy development

[Identify any EMM policies that need to be developed, the timing of these activities and who will undertake them. Outline the process for the policies to be endorsed by senior management, how the policies will be disseminated and how they will be referenced in the EMM communications material.
See Section 4.3 of the Guide to Safe Implementation for more details on policy development.
Cross-reference any policy development activities to the baseline EMM implementation project plan in Section 4 of this template.]
2.3.4
Implementation sequence planning

[Outline the proposed EMM implementation sequence, including any pilot wards, the duration of the pilots, and any evaluation and refinement activities prior to EMM rollout.

Consider the EMM implementation sequence carefully — the EMM toolkit considers a range of options. Provide the rationale for implementation sequence decisions so that stakeholders understand the basis for the EMM implementation rollout.
See Section 4.4 of the Guide to Safe Implementation for a range of options for implementation sequence planning.]
2.3.5
Change management planning

[Outline the approach to change management (e.g. Kotter’s eight-stage process; see Box 4.5 of the Guide to Safe Implementation) and whether change management activities will be undertaken in-house or by a third-party organisation.

Develop a change management plan that considers:

stakeholder analysis
stakeholder engagement strategies

communication plans in relation to change management

change readiness assessments

numbers and identities of the EMM clinical champions and change agents

the responsibilities of each person or group in delivering the change management plans.

See Section 4.5 of the Guide to Safe Implementation for more detail on change management planning.

Templates supporting change management planning include the stakeholder analysis and stakeholder map (Table 2.1 and Figure 2.1), and the communications plan (see Section 2.3.9).
Cross-reference change management activities to the baseline EMM implementation project plan in Section 4 of this template.
Complete the following template for each stakeholder group in the hospital or organisation.]

Table 2.1
Stakeholder analysis

	Stakeholder
	Stake in the project
	Potential impact on project
	What does the project expect the stakeholder to provide?
	Perceived attitudes and risks
	Stakeholder management strategy
	Responsibility

	Senior medical staff
	Medium
	Critical
	Use of EMM, and active encouragement and support for EMM use by junior medical staff
	Risk of not using and influencing uptake and use by junior medical staff
	Identify clinical champions to make the case with their peers

Involve CEO in negotiating required project outcome

Ensure an optimised fast and efficient EMM prescribing process

Emphasise downstream benefits
	Director of Medicine

Chief executive

EMM system vendor

EMM project team


CEO = chief executive officer; EMM = electronic medication management
[Summarise the stakeholder analysis on the stakeholder map. It may be useful to colour-code stakeholders, showing advocates and supporters in green, blockers and critics in red, and others who are neutral in orange. The position of a stakeholder on the grid will determine the actions required to engage them.]

[image: image2.jpg]Keep Manage
satisfied closely

*x

X

Keep
informed

X





Figure 2.1
Example stakeholder map

2.3.6
Evaluation planning

[Wherever possible, include evaluation activities in the EMM plans to measure and compare medication safety before and after implementation of the EMM system.

Evaluation components should include: 

an evaluation framework

expected outcomes following implementation of the EMM system

baseline indicators

evaluation activities

EMM implementation checkpoint reviews

post-implementation review planning.
See Section 4.6 of the Guide to Safe Implementation for more detail on evaluation planning.

Templates supporting evaluation include the evaluation framework (Table 2.2) and baseline indicators table (Table 2.3).

Cross-reference evaluation planning activities to the baseline EMM implementation project plan in Section 4 of this template.]

Table 2.2
Evaluation framework

	Expected outcome
	Indicator
	Subindicators
	Measure(s)
	Potential data sources
	Activity for data collection
	Time points for measurement

	Improved quality and safety in medicines use
	Reduced AMEs
	Prescribing errors by number, type, severity, patient volume, bed-days, total LOS
	Number of prescribing errors by type and severity

Number of patients

Number of bed-days

Total LOS
	Medication charts

Hospital issues and risk reporting (sentinel events)

Review of medication incidents and AMEs
	Audit of medication charts for a defined time period

Review of sentinel events
	Pre-implementation

Post-implementation

Ongoing monitoring

	
	
	Administration errors, etc.
	
	
	
	

	
	Increased adherence to guidelines
	
	
	
	
	


AME = adverse medicine event; LOS = length of stay

Table 2.3
Example of baseline indicators for paper-based charts and expected changes when using an EMM system

	Paper-based chart indicator
	Expected changes in an EMM system 

	Whether error-prone abbreviations were present in the medication order
	Error-prone abbreviations will not be configured in the EMM system, so this indicator will be 100%

	Whether the indication was documented
	Where recording of the indication is not mandatory, a report from the EMM system of the number of medication orders without indication recorded, sorted by prescriber, by specialty or by class of medicine, is to be used for follow-up education and training

	Whether the medication order was clearly legible 
	Legibility will not be an issue in the EMM system, so this indicator will be 100%

	Whether the prescriber and pharmacist had initialled the medication order
	Prescriber signatures will be defaulted within the EMM system and a report will indicate the extent to which pharmacists have reviewed medication orders

	Whether the nurse or midwife had initialled administration of the medicine
	The signature of nurses and midwives administering medications will be defaulted within the EMM system

	Whether the non-administering codes were used correctly
	Correct use of non-administering codes will need to be checked against other information, such as progress notes in the medical record, in a post-implementation case note audit for patients

	Whether allergies and adverse drug reactions were recorded
	The EMM system can make recording allergy and adverse drug reaction information mandatory at the time of prescribing, so this indicator would be 100%
Where recording of the indication is not mandatory at the time of prescribing, a report from the EMM system of the number of patients without allergy and adverse drug reaction information recorded is to be used for follow-up education and training

	Whether the number of medication charts identified was correct
	The number of paper medication charts recorded in the EMM system is to be validated against the number of paper medication charts in the medical record

	Whether telephone orders were validated or countersigned by the prescriber
	Prescribers will ideally access the EMM system remotely, so telephone orders will no longer be required
The extent to which telephone orders are validated or countersigned by the prescriber will depend on the EMM system workflow facilities and whether the system supports telephone orders without subsequent validation or countersigning

	Whether the patient medicines information in the discharge summary reflected medicines on admission, medicines prescribed during the admission and medicines on discharge, and listed reasons for any changes between admission and discharge
	Alignment of patient medicines information in the EMM system and the discharge summary requires a case note audit, unless the EMM system is sufficiently integrated with discharge summary production


EMM = electronic medication management
2.3.7
Benefits management activities

[Benefits management is a critical area of EMM implementation. The benefits register is a key control document to recognise planned and unplanned benefits, determine when benefits are to be measured and identify who is responsible for measuring them. The benefits register should contain both quantitative and qualitative benefits. 

The business case will include the benefits that were used to justify the investment in an EMM system and these benefits should be incorporated into the benefits register. The benefits register should be regularly updated as the expected benefits change, and should be reviewed and maintained in line with the project plan.

See Section 4.7 of the Guide to Safe Implementation for more detail on benefits management planning.

Complete the benefits register template (Table 2.4).

Cross-reference benefits management activities to the baseline EMM implementation project plan in Section 4 of this template.]

Table 2.4
Benefits register template
	Benefit
	Baseline measure
	Likely value
	Worst case
	Best case
	Responsibility and beneficiary group

	Reduction in prescribing errors
	Baseline measure to be collected before go-live for a one-month perioda
	20%
	0%
	40%
	R = Pharmacy 

B = Medical

	Reduction in administration errors
	Baseline measure before go-live from incident reporting system
	2%
	0%
	10%
	R = Pharmacy

B = Nursing and midwifery

	Elimination of time required rewriting medication charts
	Average time required to rewrite medication chart
	10 minutes per chart
	No time saving for patients on few or no medications 
	30 minutes for patients on complex medication regimes
	R = EMM system

B = Medical

	Restarting admission medications on discharge
	Implementation of admission medication functionality
	
	
	
	R = EMM system

B = Medical

	Populating the discharge medication script from the current medications list and admission medications list
	Average time required to rewrite the discharge script
	
	
	
	R = EMM system

B = Medical


B = beneficiary; R = measurement responsibility

a The hospital’s incident reporting system as an information source may be limited, recognising that most prescribing errors are identified and prevented by pharmacy before they become reportable

2.3.8
Education and training 

[EMM implementation will affect most clinical staff in the hospital, and careful planning for education and training is essential to ensure a smooth implementation.

The education and training plans may be described in detail in a separate document — in this case, summarise the education and training plans here.

Education and training plans should include:

development, sign-off and production of the education and training materials 

the availability and support of any online learning management system used to support EMM training

the approach to training; for example, vendor training or in-house training

the types of training, including informal and formal, pre-implementation, EMM system and refresher training

the number of trainers required, the length of time they will be required and their skill sets, including clinical experience 

identification and booking of training facilities, including dedicated training areas

development, availability and support of the ‘sandpit’ for consolidated learning

the timing of training in relation to EMM go-live

detailed costs, including expectations from the business regarding cross-charging for clinical time.

See Section 4.8 of the Guide to Safe Implementation for more detail on education and training.

Complete the education and training template in Table 2.5.

Cross-reference education and training activities to the baseline EMM implementation project plan in Section 4 of this template.]

Table 2.5
Education and training template

	Education and training component
	Requirement
	Responsibility
	Duration
	Cost

	Self-directed learning
	Online learning management system and support for the EMM duration
	Education and training lead
	3 months
	

	
	Education materials for the online learning management system
	Education and training team
	3 months
	

	Sandpit
	Build the sandpit environment
	ICT service provider
	1 month
	

	
	Remote access to the sandpit
	ICT telecommunications manager
	1 month
	

	Education and training collateral
	Introductions
EMM overview
Medication safety
Expected benefits
Implementation challenges (managing expectations)
	Education and training team
	1 month
	

	
	EMM system training modules
	Education and training team
	3 months
	

	
	EMM demonstrations and presentations (e.g. at grand rounds)
	Education and training team
	2 months
	

	
	Posters and fact sheets
	Education and training team
	2 months (including production time)
	

	
	Evaluation feedback and surveys
	Education and training team
	1 month
	

	Trainers
	4 people for 1 year
	Education and training lead
	4 months to advertise and fill posts
	

	Training facilities
	2 rooms for 1 year
	Education and training lead
	3 months to identify and equip
	

	Training schedule
	Overview sessions for all staff
	Education and training team
	1 hour
	

	
	Role-based training
	Education and training team
	3 hours
	


EMM = electronic medication management; ICT = information and communications technology
2.3.9
Project communications

[The stakeholder analysis (see Table 2.1) and proposed EMM project schedule will inform the communications plan.

See Section 4.9 of the Guide to Safe Implementation for more detail on project communications.

Complete the communication plan template in Table 2.6.

Cross-reference communication activities to the baseline EMM implementation project plan in Section 4 of this template.]

Table 2.6
Communications plan template

	Target audience
	Communication typea
	Stakeholder
(primary or secondary)
	Responsibility
	Key messages
	Communication modeb
	Timingc
	Frequencyd

	All staff
	Project announcement
	Both
	Project team
	EMM is coming soon
	Posters
	3 months before go-live
	Once

	All clinical staff
	Project announcement
	Primary
	Project clinicians
	Medication safety
	Posters, CEO newsletter
	3 months before go-live
	Once

	Prescribers
	Project update
	Primary
	Lead medical staff
	Medication safety
	Grand rounds
	2 months before go-live
	Monthly


CEO = chief executive officer; EMM= electronic medication management
a For example, project update, project announcement

b For example, email, phone, face to face, meetings

c Project stage or data range during which communication applies

d For example, daily, weekly, fortnightly, monthly, once
2.3.10
Quality management

[Describe the quality assurance process for project deliverables, including responsibilities for undertaking quality reviews. See Section 4.10 of the Guide to Safe Implementation for more detail on quality management.
Use the quality register in Table 2.7 to itemise planned and actual quality activities. As a minimum, review the deliverables identified in the EMM toolkit and complete a quality record for each deliverable. For each deliverable, identify the quality method, the reviewers, the approvers, the scheduled and actual review dates, and the outcome of the quality activity.

Use the quality checklist (Table 2.8) to manage quality deliverables and sign off.

The PRINCE2 project management methodology includes a quality review technique that could be usefully applied to the EMM implementation.
Cross-reference quality management activities to the baseline EMM implementation project plan in Section 4 of this template.]
Table 2.7
Quality register template

	Ref
	Item
	Quality method
	Produced by
	Reviewed by
	Approved by
	Results
	Scheduled and actual quality activities

	[X]
	IPS
	Document review
	Project manager
	Project team
	Project board
	Approved (and date)
	Held dd/mm/yy

	
	PAS interface specifications
	Document review
	PAS vendor
	Interface lead
	Technical project assurance team
	Scheduled (and date)
	Scheduled dd/mm/yy

	
	EMM hardware
	Capacity test
	ICT service provider
	Technical project assurance team
	Senior user (technical)
	Not yet scheduled
	Unscheduled

	[etc.]
	
	
	
	
	
	
	


EMM = electronic medication management; ICT = information and communications technology; IPS = implementation planning study; PAS = patient administration system

Table 2.8
Quality checklist
	Quality management and project delivery sign-off
	Complete

	EMM business case
	Yes
	No
	Partial
	N/A

	EMM system functional specifications
	Yes
	No
	Partial
	N/A

	Tender documentation before its release
	Yes
	No
	Partial
	N/A

	Contract with the selected EMM system vendor
	Yes
	No
	Partial
	N/A

	IPS
	Yes
	No
	Partial
	N/A

	Project control documents
	Yes
	No
	Partial
	N/A

	Software development enhancement specifications
	Yes
	No
	Partial
	N/A

	EMM system interface specifications
	Yes
	No
	Partial
	N/A

	Change control requests
	Yes
	No
	Partial
	N/A

	EMM process maps
	Yes
	No
	Partial
	N/A

	New software configured, tested and determined as fit for purpose
	Yes
	No
	Partial
	N/A

	EMM system build documentation
	Yes
	No
	Partial
	N/A

	UAT strategy and plans
	Yes
	No
	Partial
	N/A

	UAT scripts
	Yes
	No
	Partial
	N/A

	Education and training materials
	Yes
	No
	Partial
	N/A

	EMM communication strategy, plans and tools
	Yes
	No
	Partial
	N/A

	Scope and content of the evaluation activities
	Yes
	No
	Partial
	N/A

	Ongoing governance arrangements for EMM on completion of the implementation rollout
	Yes
	No
	Partial
	N/A

	Service-level agreements between the EMM project and third parties
	Yes
	No
	Partial
	N/A

	[insert other quality management and project delivery sign-off items as necessary]
	
	
	
	


EMM = electronic medication management; IPS = implementation planning study; N/A = not applicable; UAT = user acceptance testing
[Use the implementation timeline template in Table 2.9, to summarise and plan timelines for each stage.]

Table 2.9
Implementation timeline template
	
	Timeline (weeks)

	Task
	1
	2
	3
	4
	5
	6
	7
	8
	9
	10
	11
	12
	13
	14

	Planning stage
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	Implementation planning study
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	Business process mapping and redesign
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	EMM policy development
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	Implementation sequence planning
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	Change management planning
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	Evaluation planning
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	Benefits management planning
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	Build stage
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	Development of training materials
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	[etc.]
	
	
	
	
	
	
	
	
	
	
	
	
	
	


EMM = electronic medication management

2.4
EMM system build and configuration activities
The EMM system build and configuration activities focus on delivering the technical elements of the EMM system. Activities include: 

designing and acquiring technical infrastructure 
developing software 

building the technical environments

non-functional testing

configuring the EMM system content

developing interfaces with key support systems

user acceptance testing (UAT).

[See Chapter 5 of the Guide to Safe Implementation for more detail of EMM system build and configuration.]

2.4.1
Design and acquisition of technical infrastructure 
[Describe each of the activities required to build the EMM technical infrastructure and the responsibilities for these activities. Explain how the technical infrastructure will be developed and validated by technical stakeholders to ensure that the proposed infrastructure aligns with the organisation’s other technical infrastructure services.

Include a diagram that itemises each of the components that make up the infrastructure, including centralised hardware, the use of multiple data centres (where available), resilient components, network connectivity and network resilience.
Where technical infrastructure needs to be acquired, identify responsibilities, timelines and the reporting relationships between this project and the EMM system implementation. 

There are no specific templates for this component. See Section 5.1 of the Guide to Safe Implementation for more detail on technical infrastructure.
Cross-reference EMM design and technical infrastructure activities to the baseline EMM implementation project plan in Section 4 of this template.]
2.4.2
Software development

[In broad terms, describe the main areas where software development is required, and who is responsible for delivering each component of software.

Include any software elements to be delivered by other third-party suppliers of systems that will interface with the EMM system, as well as in-house software development activities (e.g. developing interfaces between EMM and other in-house systems).

It is important to demonstrate a tight relationship between the original requirements and the software deliverables. Explain how the requirements identified in the tender specifications or future-state process maps will be used to track the software development required. Describe how these requirements will be converted into technical specifications by the EMM supplier and subsequently validated by the EMM project team. Consider how these requirements will populate the traceability matrix and be used to develop the UAT scripts.

See Section 5.2 of the Guide to Safe Implementation for more detail on software development.

Complete the traceability matrix in Table 2.10 and keep it up to date as UAT and non-functional testing progresses.

Cross-reference software development activities to the baseline EMM implementation project plan in Section 4 of this template.]
Table 2.10
Traceability matrix template

	Reference
	Functional or nonfunctional
	Requirement description
	Design document reference
	UAT reference 
	User acceptance validation
	Comments

	[X] 
	Functional
	Interface with pharmacy dispensing system
	[X]
	Scripts 45–97
	Passed
	Refer to UAT script documentation for details

	 [X]
	Non-functional 
	Performance testing EMM hardware
	Technical infrastructure design
	Scripts 117–130
	 
	 

	 [X]
	Non-functional
	Replication failover
	Technical infrastructure design
	N/A
	Passed 
	Failover test performed dd/mm/yy

Results reviewed and approved by technical project assurance team on dd/mm/yy

	 [etc.]
	 
	 
	 
	 
	 
	 


EMM = electronic medication management; N/A = not applicable; UAT = user acceptance testing
2.4.3
Building the technical environments

[List the number of different EMM environments that are required (e.g. production, training, test, sandpit environments).
For each environment, identify the assumptions and expectations regarding the size, use and support of each environment, and responsibilities for installation and ongoing operation. For example, ICT might build the training or sandpit environment, but it may be managed by the EMM training team.

It is particularly important that the environments are sized correctly, based on the expected volume of users and transactions, and to be clear if any of the environments need to be accessible from locations that are external to the organisation’s network.

Consider the following questions:

Will the training environment need to be refreshed and, if so, how often?
How will configuration changes be managed across production, training and sandpit environments?
What is the change control procedure that will ensure the environments are aligned and who has responsibility for managing this?

There are no specific templates for this component. See Section 5.3 of the Guide to Safe Implementation for more detail on building the technical environments.
Cross-reference building the technical environment activities to the baseline EMM implementation project plan in Section 4 of this template.]
2.4.4
Non-functional testing

[Non-functional testing is an activity that is often overlooked, but it is essential for identifying and measuring the technical expectations for the EMM system to ensure technical compliance and acceptance. Examples of non-functional test requirements include system performance measures, the use of active directory, single sign-on requirements and replication failover.

Explain how the technical requirements identified in the tender specifications will populate the traceability matrix and be used to develop the non-functional UAT scripts. It is important to demonstrate a tight relationship between the original requirements and the testing of the non-functional deliverables.

See Section 5.4 of the Guide to Safe Implementation for more detail on non-functional testing.

Update the traceability matrix template (Section 2.4.2) with the non-functional requirements and the results of the non-functional testing.

Cross-reference non-functional testing activities to the baseline EMM implementation project plan in Section 4 of this template.]
2.4.5
Configuration of EMM system content

[Describe how the EMM configuration (EMM content) will be managed, including responsibilities. Describe how governance and quality assurance are involved in review and sign-off on configuration deliverables. Describe the change control process for updating the configuration records over time that ensures any changes are notified to those managing UAT scripts, education and training, communications and environment management.

List each of the areas of the EMM system that will require configuration, indicating responsibility for the content specification, its review, configuration within the EMM, and validation and sign-off.

It is important to expose EMM users to the configured content of the EMM through pre-implementation awareness activities before formal EMM training. Describe how this will occur.

There are no specific templates for this component. See Section 5.5 of the Guide to Safe Implementation for more detail on configuring the EMM system content.
Cross-reference EMM configuration activities to the baseline EMM implementation project plan in Section 4 of this template.]
2.4.6
Developing interfaces to key systems

[Interfacing between clinical systems is a specialised activity that will require collaboration between the EMM system supplier, third-party system suppliers and possibly in-house technical teams.

This is an important area of the IPS and it may be sufficient to simply cross-reference the appropriate sections of the IPS here.

It is essential that interface planning includes the activities required to:

specify, review and sign off the interface specifications

test each interface informally as well as formally once developed

implement formal change control procedures to document test outcomes, decisions and any changes to the interface

perform end-to-end testing of the interfaces.

Identify resources for testing the interfaces by third-party suppliers or in-house teams supporting the following systems:

the patient registration system

the pharmacy dispensing system

the pathology results reporting system

any system managing allergies and alerts.

There may be additional specialist systems that require interfacing to the EMM system, including chemotherapy management, intensive care, high-dependency charting or monitoring systems.

There are no specific templates for this component. See Section 5.6 of the Guide to Safe Implementation for more detail on system interfaces.
Cross-reference interface development and testing activities to the baseline EMM implementation project plan in Section 4 of this template.]
2.4.7
User acceptance testing 

[Outline the UAT process, the number of planned UAT cycles, and the resources required to develop the test scripts and undertake the UAT process. Larger organisations may have established UAT documentation, in which case these should be used and cross-referenced here.

Ensure that the UAT scripts are cross-referenced in the traceability matrix, along with the outcome of the UAT process.

Table 2.11 is a template for developing the UAT scripts. See Section 5.7 of the Guide to Safe Implementation for more detail on UAT.
Cross-reference UAT activities to the baseline EMM implementation project plan in Section 4 of this template.]
Table 2.11
User acceptance testing (UAT) script template

	Test script # 1 

	Description: New medication order

	Script reference
	Procedure
	Expected result
	Actual result
	Pass/Fail
	Criteria and reference
	Comments

	1.01
	Select patient
	Patient record displayed
	Patient record displayed
	(
Pass
	(
Fail
	Enter patient hospital no.: B99999 (for patient Mr John Dow)
	

	1.02
	Select the ‘new medication order’ function
	Prescribing function displayed
	Prescribing function displayed
	(
Pass
	(
Fail
	
	

	1.03
	Select the required medicine by typing the first few letters of the medicine until the required medicine is displayed
	Medicine requested displayed
	Required medicine not in the list
	(
Pass
	(
Fail
	Enter erythromycin
	Check content of medicine entries in the database and rerun script


2.5
EMM system implementation and go-live activities
The following activities are required to ensure a smooth transition from an EMM project environment to EMM go-live:

developing an implementation checklist
establishing the project control centre

defining go-live roles and responsibilities

defining pre- and post-go-live tasks

preparing an escalation strategy (if things go wrong)
managing the transition in a staged EMM implementation

developing a rollback and project suspension strategy

developing a project team exit strategy and transition to support.
[See Chapter 6 of the Guide to Safe Implementation for more detail on implementation and go-live activities.]

2.5.1
Implementation checklist
[The purpose of the implementation checklist is to ensure that all activities have been completed and passed their quality review cycle before starting go-live activities.

Complete and update the implementation template checklist in Table 2.12.

Cross-reference the implementation checklist activities to the baseline EMM implementation project plan in Section 4 of this template.]
Table 2.12
Implementation planning checklist

	Stages and activities
	Tasks
	Achieved

	Stage 1 — Project initiation and product selection

	Initial scoping
	Scope objectives of implementation
	

	
	Determine organisational change readiness
	

	
	Sign off project scope 
	

	Business case
	Conduct needs analysis
	

	
	Identify options
	

	
	Sign off business case
	

	Funding approval
	Sign off funding 
	

	Governance and management
	Set up governance
	

	
	Appoint project team
	

	
	Develop project plan
	

	
	Develop project schedule
	

	
	Set up cost centre
	

	Product evaluation and selection
	Develop procurement plan
	

	
	Determine single or multiple vendor
	

	
	Develop EMM specifications
	

	
	Establish tender evaluation panel
	

	
	Develop tender 
	

	
	Evaluate tenders
	

	
	Sign off tender approval 
	

	Contract management
	Develop contract management plan
	

	
	Monitor performance
	

	
	Evaluate service provider
	

	Stage 2 — Implementation planning

	IPS
	Sign off IPS
	

	Business process mapping and redesign
	Develop current-state maps
	

	
	Develop future-state maps
	

	Policy development
	Develop EMM policies
	

	Implementation sequence planning
	Develop implementation sequence plan
	

	Change management planning
	Conduct stakeholder analysis
	

	
	Define engagement strategies
	

	
	Conduct change readiness assessment
	

	
	Address stakeholder concerns
	

	
	Identify champions
	

	Evaluation planning
	Develop evaluation framework
	

	
	Define expected outcomes
	

	
	Define baseline indicators
	

	
	Conduct evaluation activities
	

	
	Conduct checkpoint and milestone reviews
	

	
	Prepare post-implementation review
	

	
	Sign off evaluation framework 
	

	Benefits management planning
	Develop benefits management plan
	

	Education and training planning
	Plan education and materials
	

	
	Plan training and materials
	

	
	Develop training courses
	

	
	Identify training times and space
	

	
	Identify timing of training
	

	Communications planning
	Develop communications plan
	

	
	Develop communication tools
	

	
	Sign off communications plan 
	

	Quality management
	Identify quality management processes
	

	
	Develop quality management tools
	

	Final approval of checklist before build phase
	

	Stage 3 — System build and configuration

	Acquisition of technical infrastructure
	Acquire technical infrastructure
	

	Software development
	Develop software
	

	Technical environment building
	Build technical environment
	

	Non-functional testing
	Complete non-functional testing
	

	Configuration of system content
	Configure system content
	

	Development of interfaces
	Develop interfaces
	

	UAT
	Develop test scripts 
	

	
	Conduct informal UAT process
	

	
	Conduct break testing
	

	
	Conduct formal UAT process
	

	
	Conduct end-to-end testing 
	

	
	Develop traceability matrix
	

	System configuration sign-off
	

	Stage 4 — Implementation and go-live

	System demonstration
	Demonstrate system
	

	Communication
	Communicate implementation plans
	

	Training of champions
	Train champions
	

	Workforce training
	Educate and train workforce 
	

	Project control centre
	Establish project control centre
	

	Go-live roles and responsibilities
	Define go-live roles, responsibilities and tasks
	

	Strategy development
	Define escalation strategy
	

	
	Define rollback and suspension strategies
	

	
	Define project team exit strategy
	

	
	Define transition to support
	

	Go-live sign-off
	

	Stage 5 — Ongoing operations

	Post-implementation review
	Conduct post-implementation review
	

	Monitoring, evaluation and refinement
	Develop risk protocols and tools
	

	
	Develop issue protocols and tools
	

	
	Develop error protocols and tools
	

	
	Continually evaluate the system
	

	
	Continually adapt the system
	

	
	Develop process for database management and maintenance
	

	
	Develop processes for software upgrades
	

	
	Sign off changes to system 
	

	Education and training
	Develop refresher training
	

	
	Develop targeted training
	

	Vendor support
	Ensure ongoing vendor support
	

	Benefits realisation
	Monitor benefits realisation
	

	Change management
	Analyse stakeholders 
	

	
	Develop engagement strategies
	

	
	Change readiness assessments
	

	
	Address stakeholder concerns
	

	
	Identify champions
	

	Benefits management
	Plan benefits management 
	


EMM = electronic mediation management; IPS = implementation planning study; UAT = user acceptance testing
2.5.2
Project control centre
[Outline the activities to be undertaken in setting up the project control centre.

There are no templates associated with this activity. See Section 6.2 of the Guide to Safe Implementation for more detail on the project control centre.
Cross-reference project control centre activities to the baseline EMM implementation project plan in Section 4 of this template.]
2.5.3
Go-live roles and responsibilities
[Outline the roles and responsibilities of the immediate project team and frontline clinical staff, including clinical champions and expert users during go-live.

There are no templates associated with this activity. See Section 6.3 of the Guide to Safe Implementation for more detail on go-live roles and responsibilities.]
2.5.4
Pre- and post-go-live tasks
[Outline the activities to be undertaken to achieve all pre- and post-go-live tasks. Example tasks include:

checking the installation and use of all devices, including printers

ensuring the availability of wireless connections wherever EMM will be used (so there are no ‘black spots’)

producing the project team roster that ensures around-the-clock support during the go-live period

identifying clinical champions and expert users for each area

ensuring go-live communications materials are available. 

There are no templates associated with this activity. See Section 6.4 of the Guide to Safe Implementation for more detail on pre- and post–go-live tasks.
Cross-reference pre- and post-go-live tasks to the baseline EMM implementation project plan in Section 4 of this template.]
2.5.5
Escalation strategy
[Outline the activities needed to develop, communicate and sign off the escalation strategy so that all people are clear on their roles and responsibilities.

There are no templates associated with this activity. See Section 6.5 of the Guide to Safe Implementation for more detail on the escalation strategy.
Cross-reference escalation strategy activities to the baseline EMM implementation project plan in Section 4 of this template.]
2.5.6
Managing the transition in a staged implementation
[Outline the policy-related activities to manage the transition from paper to electronic medication charts. Ensure these activities are addressed in education, training and communication activities so that all clinical staff are clear about how to manage the transition from paper to EMM and vice versa.

There are no templates associated with this activity. See Section 6.6 of the Guide to Safe Implementation for more detail on managing the transition in a staged implementation.
Cross-reference transition activities to the baseline EMM implementation project plan in Section 4 of this template.]
2.5.7
Rollback and project suspension strategy
[Outline the activities needed to develop, communicate and sign off the rollback and project suspension strategy so that everyone is clear on their roles and responsibilities.

Cross-reference rollback and project suspension activities to the baseline EMM implementation project plan in this template.

There are no templates associated with this activity. See Section 6.7 of the Guide to Safe Implementation for more detail on rollback strategies.]
2.5.8
Project team exit strategy and transition to support
[Outline the exit strategy for the project team and a plan for transitioning EMM to support. Larger organisations may have checklists or templates that require completion in the planning and execution of the transition to support.

There are no templates associated with this activity. See Section 6.8 of the Guide to Safe Implementation for more detail on the project team exit strategy and transition to support.
Cross-reference transition to support activities to the baseline EMM implementation project plan in Section 4 of this template.]
3
EMM project governance
Project governance is a key aspect for successful implementation of an electronic medication management (EMM) system. The complexity of EMM system implementation is reflected in the governance structure required for successful implementation. An example project governance structure is outlined in Figure 3.1. 
[The rest of this section, including the figure, should be updated to include all aspects of the local governance structure. A template for terms of reference and minutes is provided in Appendix 2, and a project status report template is provided in Appendix 3. See Section 3.4 of the Guide to Safe Implementation for more detail on EMM project governance.]

[image: image3.jpg]Hospital
executive

Drug and
therapeutics
committee

EMM system EMM system
project manager project board

EMM system
reference group

EMM system
vendor

Chief executive

EMM system officer

project team

Pharmacy

Director of subgroup

medicine

Medical

Director of subgroup

pharmacy

Nursing
subgroup

lied health Allied health
Allied healt subgroup

Safety and Safety and quality
quality subgroup

o
subgroup

Director of
nursing and
midwifery

Chief information

Safety and officer

quality

Director of
ICT services finance/Chief
financial officer

Director of
clinical governance

Medical records

EMM software
vendor

Education EMM system project EMM system project Subgroups
and training board membership reference group (unidisciplinary
coordinator (schedule, budget, risks and issues) (multidisciplinary operational issues) operational issues)




Figure 3.1
Example project governance structure
[Complete the roles matrix in Table 3.1 for each of the individuals and groups in the project governance structure.]
Table 3.1
Roles matrix template

	Individual or group
	Roles
	Responsibilities

	EMM project board


	[insert a high-level view of the role of the individual or group]
	[insert the individual’s responsibilities or a summary of a group’s terms of reference]

	EMM reference group
	
	

	[insert all relevant individuals and groups]
	
	


EMM = electronic medication management
3.1
EMM project board

[Outline:

structure

membership

roles

relationship with other groups within the EMM implementation governance structure

relationship with the hospital executive or any higher level program management governance structure

terms of reference 

frequency of meetings.]
3.2
Roles of senior stakeholders

[Outline the detailed responsibilities of each project board member. PRINCE2 provides detailed descriptions of the roles and responsibilities of senior stakeholders.]   

3.3
EMM project team

[Adapt and complete Table 3.2 with details of the project team.]

Table 3.2
EMM project team

	Title
	Name
	Role

	Project sponsor
	
	

	Project manager
	
	

	Project team member
	
	

	Project team member
	
	

	[etc.]
	
	


3.4
EMM reference group

[Outline:

structure

membership

roles
relationship with other groups within the EMM implementation governance structure

terms of reference 
frequency of meetings.]
3.5
Specialty subgroups and project assurance teams
3.5.1
Drug and therapeutics committee
[Outline:

structure

membership

roles
relationship with other groups within the EMM implementation governance structure

terms of reference 

frequency of meetings.]
3.5.2
Pharmacy subgroup

[Outline:

structure

membership

roles
relationship with other groups within the EMM implementation governance structure

terms of reference 

frequency of meetings.]
3.5.3
Medical subgroup

[Outline:

structure

membership

roles
relationship with other groups within the EMM implementation governance structure

terms of reference 

frequency of meetings.]
3.5.4
Nursing and midwifery subgroup
[Outline:

structure

membership

roles
relationship with other groups within the EMM implementation governance structure

terms of reference 

frequency of meetings.]
3.5.5
Allied health subgroup
[Outline:

structure

membership

roles
relationship with other groups within the EMM implementation governance structure

terms of reference 

frequency of meetings.]
3.5.6
Safety and quality subgroup

[Outline:

structure

membership

roles
relationship with other groups within the EMM implementation governance structure

terms of reference 

frequency of meetings.]
3.5.7
Information and communications technology (ICT) subgroup

[Outline:

structure

membership

roles
relationship with other groups within the EMM implementation governance structure

terms of reference 

frequency of meetings.]
4
Project plan
[A detailed project plan brings together all the components required to deliver and implement the EMM system.

Project planning is only useful within a reasonable planning horizon. Plans for the first stage of the EMM implementation — the implementation planning study — should be in sufficient detail to properly track project activities, dependencies and resources. Plans for subsequent stages will be less well defined initially, and will become more detailed over time.
Use the implementation checklist in Table 2.12 (Section 2.5.1) when developing the project plan to ensure all aspects of the EMM implementation are considered and incorporated. Number the phases and the tasks within each phase for ease of cross-referencing (e.g. Phase 1 — Project initiation will include tasks 1.1, 1.2, 1.3, etc.). 
Include the full EMM implementation project plan in this section.]

4.1
Key phases and milestones
[Identify the main project phases and project milestones that are detailed in the project plan. The purpose of this section is to convey key aspects of the project plan to stakeholders without needing to refer to the detail of the project plan itself.

Complete the phases and milestones template in Table 4.1.]
Table 4.1
Phases and milestones template

	Plan reference
	Phases
	Milestones
	Expected date

	1.1
	Project initiation phase
	Confirm project governance arrangements
	July 20xx

	1.2
	
	Confirm project reporting arrangements
	July 20xx

	1.3
	
	Confirm change control arrangements
	July 20xx

	1.4
	
	Confirm delegated authorities
	July 20xx

	1.5
	
	Sign off work package descriptions
	August 20xx

	1.6
	
	Establish benefits register
	September 20xx

	1.7
	
	Sign off evaluation plans
	September 20xx

	1.8
	
	Sign off change management plans
	September 20xx

	1.9
	
	Sign off communication plans
	October 20xx

	1.10
	
	Establish risk register
	October 20xx

	1.11
	
	Establish issues register
	October 20xx

	1.12
	
	Develop baseline project plans
	November 20xx

	2.1
	Implementation planning study phase
	
	January–March 20xx

	3.1
	Software development phase
	
	April–June 20xx

	4.1
	Acquire technical infrastructure phase
	
	

	[etc.]
	
	
	


4.2
Budget

[Complete the example template in Table 4.2 to identify the budget for the EMM system implementation in sufficient detail to be useful to stakeholders.

This high-level budget information will provide stakeholders with an overview of the key cost elements of the EMM implementation, such as the budgetary provision for training, the cost of the EMM project team and resources earmarked for change management.

These high-level costs should be substantiated with detailed spreadsheets providing cost breakdowns for all aspects of the EMM implementation.]
Table 4.2
Budget and expenditure monitoring template

	Budget category
	Budget item
	Budget
	Actual to date
	Estimate to completion
	At completion

	EMM project team
	Project manager
	
	
	
	

	
	Project team
	
	
	
	

	
	Project team facilities
	
	
	
	

	EMM application software
	EMM licenses
	
	
	
	

	
	EMM application software
	
	
	
	

	
	EMM software enhancements
	
	
	
	

	Third-party software
	Patient administration system interface
	
	
	
	

	
	Pathology interface
	
	
	
	

	
	Pharmacy dispensing interface
	
	
	
	

	
	Discharge summary interface
	
	
	
	

	EMM implementation (vendor)
	IPS
	
	
	
	

	
	EMM vendor implementation services
	
	
	
	

	
	Interfaces and integration specialists
	
	
	
	

	
	In-house ICT support
	
	
	
	

	In-house costs
	UAT
	
	
	
	

	
	EMM training (including trainers and training collateral)
	
	
	
	

	Hardware costs
	Computers and mobile devices and telecommunications infrastructure (managed as a separate project)
	
	
	
	

	
	Hardware infrastructure
	
	
	
	

	[etc.]
	
	
	
	
	

	Total
	
	
	
	
	


EMM = electronic medication management; ICT = information and communications technology; IPS = implementation planning study; UAT = user acceptance testing

4.3
Risk management
[Implementing an EMM system presents substantial risks that need to be managed. Risks are actively managed by the EMM project manager and are a key area for project board consideration.

See Section 3.5.4 of the Guide to Safe Implementation for more detail on risk management.

Use the risk assessment matrix in Table 4.3 to classify risks.]
Table 4.3
Risk assessment matrix
	
	
	Likelihood
	

	Impact
	Low
	Medium
	High

	High
	Priority 3

Serious impact

Low likelihood
	Priority 2

Serious impact

Medium likelihood
	Priority 1

Serious impact

High likelihood

	Medium
	Priority 4

Medium impact

Low likelihood
	Priority 3

Medium impact

Medium likelihood
	Priority 2

Medium impact

High likelihood

	Minimal
	Priority 5

Minimal impact

Low likelihood
	Priority 4

Minimal impact

Medium likelihood
	Priority 3

Minimal impact

High likelihood


[Complete the risk register template in Table 4.4, incorporating any risks identified in the EMM business case. Maintain the risk register throughout the EMM project and escalate risks to the EMM project board as required.

The project budget should contain contingency to manage project risk. Contingency should not be universally applied across the project. Risk-based contingency should be applied to those parts of the project where risk has been identified. The risk-based contingency funding should only be used to mitigate the identified risks and should not be used for any other purpose without governance approvals.]
Table 4.4
Risk register

	Risk
	Impact
	Category before mitigation
	Probability before mitigation
	Mitigation strategy
	Category after mitigation
	Probability after mitigation

	Poor system performance


	Poor uptake and use of an EMM system by clinicians


	Medium
	40%
	Predict performance metrics at the outset, based on expected user concurrency and transaction loads

Monitor performance with lead site implementations

Predict impact for remaining rollout

Budget for additional hardware to be available on standby arrangements


	Low
	10%

	Protracted implementation


	Failure to achieve the required critical mass within a reasonable timeframe


	High
	60%
	Plan for a complete rollout within a reasonable timeframe (e.g. 12 months)
Communicate to stakeholders the importance of obtaining early critical mass

Select lead sites carefully to ensure support and avoid procrastination

Ensure responsive governance so issues identified at lead sites are dealt with quickly


	Medium
	30%

	[etc.]
	
	
	
	
	
	


EMM = electronic medication management

4.4
Issue management
[Issues will inevitably occur throughout the EMM implementation — these should be formally managed and escalated as appropriate. See Section 3.5.4 of the Guide to Safe Implementation for more detail on issue management.
Maintain the issue register template in Table 4.5 throughout the EMM project.]
Table 4.5
Issue register

	Date
	Issue description
	Identified by
	Priority
	Reported to 
	Action(s) to be taken 
	Person(s) responsible for action(s)

	dd/mm/yy
	Push-back from medical staff due to additional time impost
	Project manager
	High
	Project sponsor

Director of medical services (senior user)
	Investigate complaints

Arrange meeting with relevant medical staff

Present the safety and quality case

Present the downstream benefits

Explain reduction in time required once emergency department is using EMM
	Project manager in conjunction with the director of medical services and clinical champions (medical champions)

	[etc.]
	
	
	
	
	
	


EMM = electronic medication management
5
Ongoing operations
Electronic medication management (EMM) is not a ‘set and forget’ system and, once implemented, its maintenance becomes a part of continuing hospital operations. The ongoing operation of the EMM system requires resources to ensure that it remains up to date, functional and safe.

This section outlines the requirements for ongoing operations of the EMM system.
[See Chapter 7 of the Guide to Safe Implementation for more detail on ongoing operations.]

5.1
EMM ongoing operations
EMM ongoing operations include:
post-implementation review (PIR)
monitoring, evaluation and refinement
consolidation of education and training
vendor support

benefits measurement.
[Insert details of any other ongoing operations that will occur following implementation of the EMM system.]
5.1.1
Post-implementation review

[A PIR will assess the success of the EMM implementation, identify lessons for subsequent projects and identify areas for improving the EMM implementation. For example, the PIR may identify that the expected benefits have not been realised, or a need for additional refresher training and software improvements that would increase the usefulness of the EMM.

In this section, outline any plans for a PIR including the timing and who will undertake the review. Some organisations may commission an independent PIR to ensure objectivity.
See Section 7.1 of the Guide to Safe Implementation for more detail on the post-implementation review.]
5.1.2
Ongoing monitoring, evaluation and refinement
[Outline how the hospital will monitor, evaluate and refine the EMM system on an ongoing basis after implementation. This should include areas of ongoing evaluation, the evaluation methodology, timeline and responsibilities.
See Sections 7.2–7.5 of the Guide to Safe Implementation for more detail on ongoing monitoring and refinement.]
5.1.3
Consolidation of education and training
[Outline how the hospital will develop and implement plans to ensure education and training is consolidated after implementation, and how refresher education and training will be provided on an ongoing basis.
See Section 7.6 of the Guide to Safe Implementation for more detail on consolidating education and training.]
5.1.4
Ongoing vendor support
[Outline how the hospital will ensure ongoing vendor support and involvement in developing and refining the EMM system after implementation.
See Section 7.7 of the Guide to Safe Implementation for more detail on ongoing vendor support.]

5.1.5
Benefits measurement
[Outline how the hospital will measure and communicate the benefits of the implementation on an ongoing basis.
See Section 7.8 of the Guide to Safe Implementation for more detail on benefits measurement.]

Appendix 1
Business process maps
 [Insert current-state and future-state business process maps here.]
Appendix 2
Terms of reference and minutes template
	Committee name
	EMM project board

	Reporting to (sponsor)
	The CEO and executive team through the project sponsor

	Chairperson
	Project sponsor

	Project coordinators
	Project manager
	

	Members
	
	

	
	
	

	
	
	

	
	
	

	
	
	

	Direct report
	

	Responsibility
	The role of the project board is to effect the implementation of [insert purpose].
The project board is responsible to the hospital executive (or program executive where EMM forms part of a larger program of work) for the determination of objectives listed below (adapted from PRINCE2). 

	Objectives
	· Provide accountability for the success of the EMM implementation

· Provide direction to the project

· Delegate day-to-day management within defined tolerances

· Facilitate the integration of the project team with the functional units of the hospital

· Provide resources and authorise the release of funds

· Ensure effective decision making

· Provide visible and sustainable support for the project manager

· Ensure effective communication within the project team and with external stakeholders



	Reporting
	Issues that either affect other areas of the hospital’s business or are outside of the EMM project’s defined scope should be referred to the hospital executive (or program executive) for decision making

	Frequency of meetings 
	Meetings will be held at regular intervals and reflect the EMM implementation work program (meetings may be time based or milestone based as required by the project sponsor) 

	Agenda
	Attendance and apologies

Approval of minutes

Actions arising

Project report (schedule, expenditure, risks and issues)

New business

	Minutes



	Approval (sponsor)
	
	Signed:


CEO = chief executive officer; EMM = electronic medication management

Appendix 3
Project status report template

	Project status report

	Date: 
	Reporting period: [insert date of reporting period] 

	Hospital: 
	Project name or number:

	Report author: 
	Title: Team leader

	Program status: Green
This period

Green

Last period

Amber

Previous period

Red

Choose status from:
· green — as per schedule

· amber — within tolerances (±5%)

· red — exceeded tolerances (overdue, over budget, etc.).

	Project summary:

	Achievements and comments

	

	Milestone summary

	Milestone
	Due date
	Revised date
	Status
	Responsible team member

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	Major tasks in progress 

	Task 
	Date due
	Responsible team member

	
	
	

	
	
	

	
	
	

	
	
	

	
	
	

	Major tasks completed since last report

	Task 
	Date
	Responsible team member

	
	
	

	
	
	

	
	
	

	
	
	

	
	
	

	Major tasks running late or not started 

	Task 
	Date
	Responsible team member

	
	
	

	
	
	

	
	
	

	
	
	

	Major tasks due next period

	Task 
	Date
	Responsible team member

	
	
	

	
	
	

	
	
	

	
	
	

	
	
	

	High-priority risks 

	Description
	Impact
	Likelihood
	Outcome or mitigation

	
	
	
	

	
	
	
	

	
	
	
	

	
	
	
	

	High-priority issues
	
	

	Description 
	Logged
	Status 
	Actions

	
	
	
	

	
	
	
	

	
	
	
	

	
	
	
	

	Project expenditure (as per project budget and expenditure template)

	
	
	

	
	
	

	
	
	

	Other

	
	
	

	
	
	

	
	
	


Document name: EMM Implementation Planning Template 
Revised: 20/04/2011
60
EMED-Plan-21-VER(6Apr11).doc - d MMMM yyyy SAVEDATE  \@  
16 April 2011

60

